## Tasks
Done? | Task | Project | Priority | Week | Blocker/Notes
| Enforce tenant limits (maxPatients/maxUsers) | MyClinicDesk | Now | Week 1 | Schema has limits but API doesn't check them
| Enforce post-trial write blocking | MyClinicDesk | Now | Week 1 | Expired clinics can still write data
| Add rate limiting on registration endpoint | MyClinicDesk | Now | Week 1
| Commit 7 pending files & deploy | MyClinicDesk | Now | Week 1
| Hand product to Agen — ready to sell | MyClinicDesk | Now | Week 1 | He handles distribution
| Wire Stripe checkout for Agent Reports ($49) | SafeStreets | Next | Week 2 | Payment gate was removed — need to re-add
| Build 'first 3 free' counter + conversion flow | SafeStreets | Next | Week 2
| Publish first blog post via admin content queue | SafeStreets | Next | Week 2
| Set up content rhythm — 2 posts/week | SafeStreets | Next | Week 2 | Use admin tools already built
| Follow up on TCDC partnership | SafeStreets | Next | Week 2 | Don't block on it
| Commit 28 pending files (Lanna theme) | CM Guide | Next | Week 3
| Set up Railway + PostgreSQL for production | CM Guide | Next | Week 3 | Currently SQLite — won't scale
| Configure env vars (Stripe, Mapbox, Anthropic) | CM Guide | Next | Week 3
| Deploy + get live URL | CM Guide | Next | Week 3
| Test payment flow end-to-end ($9.99) | CM Guide | Next | Week 3
| Build personal website (who I am + 4 products) | Personal | Later |  | Simple, one page
| Research business registration (sole prop vs LLP) | Admin | Later |  | Needed for enterprise contracts
| Deploy quiz/cert improvements | Fujifilm | Later |  | Wait for Santhosh's management feedback first

## Overview
Project | Status | URL | Revenue | Current Priority | Key Blocker
MyClinicDesk | Live | myclinicdesk.com | ₹8,000 | Harden for SaaS launch | Tenant limits not enforced
SafeStreets | Live | safestreets.streetsandcommons.com | ₹0 | Re-integrate Stripe ($49 reports) | No payment gate
CM Guide | Pre-launch | Not deployed | ₹0 | Deploy to production | Infra + config, not code
Fujifilm | On hold | fujifilm-sales-production.up.railway.app | ₹0 | Wait for client feedback | Client decision pending
TOTAL REVENUE |  |  | ₹8,000

## Weekly Plan
Week | Focus | Goal
Week 1 | MyClinicDesk | Harden SaaS, deploy, hand to Agen to sell
Week 2 | SafeStreets | Monetize with Stripe + start content engine
Week 3 | CM Guide | Deploy to production with live URL